## Sheet1
KETA MUNICIPAL ASSEMBLY
2022 ANNUAL ACTION PLAN
Programme (PBB) | Sub-programme (PBB) |  | Time Frame - (2022) |  |  |  | Cost |  |  | Programme Status |  | Implementing Institution/Department
|  | Broad Activities | Q1 | Q2 | Q3 | Q4 | GoG | IGF | Others | New | Ongoing | Lead | Collaborating
DEVELOPMENT DIMENSION: ECONOMIC
TRADE AND INDUSTRY (BAC) /LED ACTIVITIES
Economic Development | Trade, Tourism and Industrial Development | Carry out Business Counselling for 40 businesses |  |  |  |  | 22000 |  |  | New |  | BAC | Businesses | 1
|  | Support 8 Entrepreneurs to Apply for the GET-P Phase 2 grant | [8 empty] | Ongoing | BAC | Businesses | 2
|  | Facilitate the Registration of Candidates for NVTI Proficiency Exams | [8 empty] | Ongoing | BAC | Businesses | 3
|  | Support 11 Women Entrepreneurs to apply for D4J | [8 empty] | Ongoing | BAC | Businesses | 4
| Trade, Tourism and Industrial Development | Conduct sensitization on GJSP | [8 empty] | Ongoing | BAC | Businesses | 5
|  | Carry out 2 No. Business Forum for Businesses |  |  |  |  | 10000 |  |  |  | Ongoing | BAC | Businesses | 6
|  | Support Productive Sectors to expand and create New Jobs( Provision of Market Stores) |  |  |  |  | 15000 |  |  | New |  | BAC | Businesses | 7
AGRICULTURE DEPARTMENT
Economic Development | Agricultural services and management | Conduct technical review meetings and TEDMAG training for AEAs @Keta | [6 empty] | 12000 |  | Ongoing | Dept. Of Agriculture | Farmers | 8
|  | Dissemination of Government policies on Planting for food on various radio stations and communities like Keta, Abor, Anyako | [6 empty] | 1500 |  | Ongoing | Dept. Of Agriculture | Farmers | 9
|  | Train and support women in alternative livelihood within the municipality | [6 empty] | 12323 |  | Ongoing | Dept. Of Agriculture | Farmers | 10
|  | Conduct farm and home visit by AEAs to sensitized farmers in new tech to improve yields | [6 empty] | 16545 |  | Ongoing | Dept. Of Agriculture | Farmers | 11
|  | Conduct pest and disease surveillance on crop and livestock across the Municipal | [6 empty] | 23223 |  | Ongoing | Dept. Of Agriculture | Farmers | 12
|  | Celebration of Municipal Farmers day |  |  |  |  | 60000 |  | 26545 |  | Ongoing | Dept. Of Agriculture | Farmers | 13
|  | Collection of data on farmers and database management | [6 empty] | 14343 |  | Ongoing | Dept. Of Agriculture | Farmers | 14
|  | Promote planting and rearing for food and jobs (field demonstration) | [6 empty] | 17655 |  | Ongoing | Dept. Of Agriculture | Farmers | 15
|  | Organize 1 field day and establish 2 conservation agriculture demonstration | [6 empty] | 12444 |  | Ongoing | Dept. Of Agriculture | Farmers | 16
|  | Procurement and distribution of Agriculture inputs |  |  |  |  | 100000 |  | 12343 |  | Ongoing | Dept. Of Agriculture | Farmers | 17
|  | Support to Modernization of Agriculture in Ghana projects/programmes |  |  |  |  | 2000 |  | 12323 |  | On-going | Dept. Of Agriculture | Farmers | 18
DEVELOPMENT DIMENSION: SOCIAL DEVELOPMENT
GOAL: CREATE OPPORTUNITIES FOR ALL GHANAIANS
SOCIAL PROTECTION PROGRAMMES
Social Services Delivery | Social Welfare and Community Development | Monitoring and follow up visits on LEAP beneficiaries on the utilization of LEAP grant in 5 communities |  |  |  |  | 10000 | 5000 |  |  | On-going | SW&CD | Assembly Members/ Tas/ LEAP Beneficiaries | 13
|  | Facilitate the renewal and repalcement of NHIS cards for 100 vulnerable persons. |  |  |  |  | 30000 |  |  |  | On-going | SW&CD | Assembly Members/ NHIS/ GHS | 14
PERSONS WITH DISABILITY (PWD) ACTIVITIES
Social Services Delivery | Social Welfare and Community Development | Enroll 90% of all registered vulnerable persons (PWDs/ LEAP Beneficiaries etc) on NHIS |  |  |  |  | 10000 | 5000 |  |  | On-going | SW&CD | Assembly Members/ NHIS/ GHS | 15
|  | Support 60% of all Registered PWDs in income generating Activities |  |  |  |  | 30000 |  |  |  | On-going | SW&CD | Assembly Members/ PWD | 16
|  | Build Capacity of 35% of all Registered PWDs |  |  |  |  | 10000 | 5000 |  |  | On-going | SW&CD | Assembly Members/ PWDs | 17
GENDER EMPOWERMENT& MAINSTREAMING
Social Services Delivery | Social Welfare and Community Development | Promote the Inclusion (20%) women on all Statutory Sub Committees |  |  |  |  | 1500 | 1000 |  |  | On-going | SW&CD | NCCE | 18
|  | Sensitize and Educate women on Domestic Violence on Radio. |  |  |  |  | 5000 | 1000 |  |  | On-going | SW&CD | Information services. Radio Stations | 19
|  | Monitor and Train WATSAN Board Members (Women) on the Importance of Safe Drinking Water |  |  |  |  | 15000 | 11000 |  |  | On-going | SW&CD | WATSAN | 20
|  | Provide Sanitary/ Kitchens/ Washrooms / Change rooms for Keta NMTC Hostel Project |  |  |  |  | 15000 | 11000 |  |  | On-going | SW&CD | KETA NMTC | 21
|  | Carry out Radio Sensitization programme on International Womens Day(On gender Equality and Non Discrimination Against Women) |  |  |  |  | 9000 | 1000 |  |  | On-going | SW&CD | NCCE | 22
CHILD RIGHT PROMOTION & PROTECTION ACTIVITIES
Services Delivery | Social Welfare and Community Development | Conduct monitoring and inspection visit to resisdentaial ( Transitional/ Shelter Homes) for children |  |  |  |  | 12000 | 1000 |  |  | On-going | SW&CD | NCCE | 23
|  | Manage 60 Family Welfare Cases |  |  |  |  | 12000 | 1000 |  |  | On-going | SW&CD | Tas | 24
EDUCATION ,YOUTH AND SPORT
Social Services Delivery | Education, Youth and Sport | Construction of 1No. 2-Unit kindergarten block at Wenyagor |  |  |  |  | 247373 |  |  | New |  | Works | GES | 25
|  | Supply of 500 No. Dual Desk to selected schools within the municipality |  |  |  |  | 200000 |  |  |  | On-going | Works | GES | 26
|  | Supply of 600 No. Mono Desk to selected schools within the municipality |  |  |  |  | 200000 | 2000 |  |  | On-going | Works | GES | 27
|  | Carry out Orientation workshop for 2022 newly posted teachers |  |  |  |  | 11009 |  |  |  | On-going | GES | Teachers | 28
|  | Carry out Continuous Professional Development Workshop for all teachers. |  |  |  |  | 9888 |  |  |  | On-going | GES | Teachers | 29
|  | Celebrate Ghana Teacher Recognition Day – Keta |  |  |  |  | 12765 |  |  |  | On-going | GES | Teachers | 30
|  | Train SHS teachers on MoE accountability dashboard |  |  |  |  | 2000 |  |  |  | On-going | GES | Teachers | 31
PUBLIC HEALTH SERVICES AND MANAGEMENT
Social Services Delivery | Public Health Services Management | Undertake supervision in 8 CHMC meetings and 2 durbars |  |  |  |  | 20000 | 2888 |  |  | On-going | GHS | Assembly Members | 32
|  | Carry out Review meeting in all health centers and the two hospital room to review activities on TB Control and strategies to increase TB case detection |  |  |  |  | 12000 | 3545 |  |  | On-going | GHS | Assembly Members | 33
|  | Carry out 12 Radio programs and 7 community durbars on maternal, neonatal and child health programs |  |  |  |  | 8000 |  |  |  | On-going | GHS | Assembly Members | 34
|  | Carry out Weekly nutrition clinics |  |  |  |  | 12000 |  |  |  | On-going | GHS | Assembly Members | 35
|  | Meet stakeholders from various shrine and traditional psychic and healer association to discuss ways to improve the uptake of the Covid 19 vaccine among their members |  |  |  |  | 11100 | 2343 |  |  | On-going | GHS | Assembly Members | 36
|  | Carry out health screening of staff and the communities within Keta Municipality during the annual Hogbetsotso festival. |  |  |  |  | 1900 |  |  |  | On-going | GHS | Assembly Members | 37
BIRTH AND DEATH REGISTRY
Social Services Delivery | Birth and death Registration Services | Register Births and Deaths in the Municipality |  |  |  |  | 1900 |  |  |  | On-going | Births and Deaths | Assembly Members | 38
ENVIRONMENTAL HEALTH /SANITATION
Social Services Delivery | Environmental Health Services | Prepare a new MESSAP (2022-2027) |  |  |  |  | 2172 |  |  |  | On-going | EHSU | MPCU | 39
|  | Undertake and Monitor Fumigation and waste management services |  |  |  |  | 3245 |  |  |  | On-going | EHSU | Zoomlion | 40
|  | Carry out Orientation for food vendors and school feeding programme contractors on nutrition |  |  |  |  | 3454 |  |  |  | On-going | EHSU | Zoomlion | 41
|  | Prosecute Sanitation Offenders |  |  |  |  | 7645 |  |  |  | On-going | EHSU | Assembly Members | 42
|  | Monitoring of community Led Total Sanitation (CLTS) in 50 communities and construction of household latrine |  |  |  |  | 2334 |  |  |  | On-going | EHSU | Assembly Members | 43
|  | Undertake and Monitor medical screening for food vendors |  |  |  |  | 2343 |  |  |  | On-going | EHSU |  | 44
|  | Management of solid waste disposal site |  |  |  |  | 80000 |  |  |  | On-going | Waste landfills ltd | EHU | 45
|  | Carry Out Monthly Clean Up Activities |  |  |  |  | 6984 |  |  |  | On-going | EHSU | Assembly Members | 46
|  | Support World Toilet Day and world environmental sanitation days |  |  |  |  | 2637 |  |  |  | On-going | EHSU | Assembly Members | 47
|  | Acquisition/Maintenance of final disposal site |  |  |  |  | 7263 |  |  |  | On-going | EHSU | Assembly Members | 48
|  | Disinfection and disinfestation of sanitary sites within the municipality |  |  |  |  | 175000 |  |  |  | On-going | EHSU | Assembly Members | 49
Development Dimension: Environment, Infrastructure And Human Settlement
Goal: Safeguard The Natural Environment And Ensure A Resilient Built Environment
Physical Planning Department
Infrastructure Delivery and Management | Physical and Spatial Planning Development | Preparation of local plans, for Vodza, Keta, Kedzi |  |  |  |  | 10000 |  |  | On-going |  | PPD | Assembly Members | 50
|  | Undertake monthly development control activities |  |  |  |  | 9000 |  |  | On-going |  | PPD | Assembly Members | 51
|  | Organize Spatial Planning and Technical Sub-Committee meetings |  |  |  |  | 10000 |  |  | On-going |  | PPD | MPCU | 52
|  | Support the Parks and Garden Unit to undertake tree planning, beautification of the environment. |  |  |  |  | 4000 | 1000 |  |  | On-going | PPD | GIZ | 53
|  | Identify, demarcate and register Assembly properties /land. |  |  |  |  | 23000 |  |  |  | On-going |  | Lands Commission | 54
|  | Expand the Street Naming and Property Addressing system programme | [5 empty] | 50000 |  |  | On-going | PPD | GIZ | 55
WORKS DEPARTMENT
Infrastructure Delivery And Management | Public Works, Rural Housing and Water Management | Monitor & inspect all projects and organize of site meetings | [8 empty] | On-going | Works Department | MPCU | 56
|  | Reshape Keta - Rose Pavillion Road |  |  |  |  | 24000 |  |  | New |  | Works Department | MPCU | 57
|  | Execute the Oeration and Maintenance Plan of KeMA |  |  |  |  | 126342 |  |  |  |  | Works Department | MPCU | 58
|  | Reshape Atiavi to Glime Road | [7 empty] | New |  | Works Department | MPCU | 59
|  | Construct 3.No Speed Ramps Keta to Aflao Road |  |  |  |  | 90000 |  |  | New |  | Works Department | MPCU | 60
|  | Carry out 2 No Sensitization programmes on Road Safety in Keta and Abor |  |  |  |  | 12000 |  | 45000 | New |  | Urban Roads | Works Dept | 61
|  | Carry out Grading works on Afife -Aborlorvi-Anyako Road |  |  |  |  | 40000 |  |  | New |  | Works Department | MPCU | 62
|  | Carry out Grass Cutting along Abor-Anyako Road |  |  |  |  | 44000 |  |  | New |  | Works Department | MPCU | 63
|  | Carry out Ditch Cleaning in the Municipality |  |  |  |  | 42222 |  |  | New |  | Works Department | MPCU | 64
|  | Carry out Construction of 12 No.Hostel at Keta NMTC |  |  |  |  | 1000000 |  |  | New |  | Works Department | MPCU | 65
|  | Complete the Renovation of old PWD yard @ Keta for other offices |  |  |  |  | 800000 |  |  |  | On-going | Works Department | MPCU | 66
|  | Construction of 1No. 14-Seater market shed @ Anlo-Afiadenyigba |  |  |  |  | 121000 |  |  |  | On-going | Works Department | MPCU | 67
|  | Construction of 1No. 6-Unit lockable stores @ Keta market, Open market Shed at Abor Commercial Hostel at Keta |  |  |  |  | 331400 |  |  | New |  | Works Department | MPCU | 68
|  | Renovate Doctors Flat |  |  |  |  | 65000 |  |  | New |  | Works Department | MPCU | 69
|  | Renovate Bungalows of Budget, Planning,Judges, MCD, MFO |  |  |  |  | 769722 |  |  |  | On-going | Works Department | MPCU | 70
DISASTER MANAGEMENT RESPONSE
Environmental Management | Disaster Prevention and Management | Carry out Coastal Disaster Reduction Education I in five (5) coastal communities; namely Kedzikope, Kedzi, Abutiakope, Adzido and Vodza. |  |  |  |  | 3637 |  |  |  | On-going | NADMO | Forestry Commission | 71
|  | Carry Out radio education on the on “Types of Floods, Causes and Mitigation Factors”. |  |  |  |  | 2736 |  |  |  | On-going | NADMO | Forestry Commission | 72
|  | Carry out Public Educations in the following four communities Abor, Dorveme, Sasieme and Asadame. on , “Alertness on Rain / Windstorms”: |  |  |  |  | 4546 |  |  |  | On-going | NADMO | Forestry Commission | 73
CLIMATE CHANGE /NATURAL RESOURCE CONSERVATION
Environmental Management | Natural Resource Conservation and Management | Undertake tree planting exercises at identify within the municipality(Green Ghana Day) |  |  |  |  | 2625 |  |  |  | On-going | Forestry Commission | MPCU/ Tas/ Assembly Members/ NADMO | 74
|  | Collaborate with Friends of the Earth NGO to restore about 6 hectares of degraded mangrove at Agortoe |  |  |  |  | 7684 | 2425 |  |  | On-going | NADMO | Friends of the Earth NGO | 75
|  | Established a central nursery of 80,000 red, white mangroves and assorted trees |  |  |  |  | 3854 |  |  |  | On-going | Forestry Commission | NADMO | 76
|  | Collaborate FC to organize sensitization programme on deforestation and forest degradation in 40 communities |  |  |  |  | 3837 |  |  |  | On-going | NADMO | Forestry Commission | 77
|  | Carry out Domestic Fire Prevention/Anti-Bush Fire educations At Abor and Atiavi. |  |  |  |  | 1172 |  |  |  | On-going | NADMO | Forestry Commission | 78
|  | Carry out 3 radio programmes to create awareness on the importance of wet lands, wildlife, wild fires and environmental protection |  |  |  |  | 15222 | 6353 |  |  | On-going | NADMO | Forestry Commission | 79
|  | Organize public education on climate change, the Effects and Adaptation at Afiadenyigba and Anyako |  |  |  |  | 25252 | 1722 |  |  | On-going | NADMO | Forestry Commission | 80
DEVELOPMENT DIMENION: GOVERNANCE, CORRUPTION AND PUBLIC ACCOUNTABILITY
GOAL: MAINTAIN A STABLE ,UNITED AND SAFE COUNTRY
CENTRAL ADMINISTRATION
Management and Administration | General Administration | Organize 2. No Town hall /stakeholders meetings on government policies, planning and budgeting |  |  |  |  | 15000 | 12999 |  |  | On-going | Central Administration | Tas/ Assembly Members | 81
|  | Collaborate with Ghana Water Company Limited (GWCL), ECG/ Community Water and Sanitation Agency (CWSA) and Small Water System (SWS) in the provision of services to the public |  |  |  |  | 15000 | 12999 |  |  | On-going | Central Administration | GWC/ CWSA/ ECG | 82
|  | Opertionalize the Client Service Unit |  |  |  |  | 15000 | 12999 |  |  | On-going | Central Administration | Client Service Officer | 83
|  | Organize Inter Sectoral Meetings |  |  |  |  | 15000 | 12999 |  |  | On-going | Central Administration | Tas/ Assembly Members | 84
|  | Organize all statutory meetings( Sub Committees/ EXECO/ General Assembly etc |  |  |  |  | 59000 | 8777 |  |  | On-going | Central Administration | Tas/ Assembly Members | 85
|  | Procure office equipment ,stationery etc |  |  |  |  | 53663 | 18282 |  |  | On-going | Central Administration | Tas/ Assembly Members | 86
|  | Organize MCE Engagement Programmes in Communities |  |  |  |  | 15443 | 10101 |  |  | On-going | Central Administration | MPCU | 87
|  | Repairs and maintenance of office vehicles |  |  |  |  | 13720 |  |  |  | On-going | Central Administration | Tas/ Assembly Members | 88
|  | Celebration of national events (independence day, farmers day, senior citizens day etc) |  |  |  |  | 8473 |  |  |  | On-going | Central Administration | Tas/ Assembly Members | 89
|  | Support the Operationalization of the Sub Structures |  |  |  |  | 245928 |  |  |  | On-going | Central Administration | Tas/ Assembly Members | 90
FINANCE AND AUDIT
Management and Administration | Finance and Audit | monitor & superve revenue collectors and organize quarterly performance review meetings |  |  |  |  | 20202 | 2522 |  |  | On-going | Finance Department | Revenue Collectors | 91
|  | Sensitize citizens on Revenue collection/tax education, tax compliance within the municipality |  |  |  |  | 12727 | 6922 |  |  | On-going | Finance Department | Revenue Collectors/ Budget | 92
HUMAN RESOURCE ACTIVITIES
Management and Administration | Human Resource Management | Sensitize officers on LGS Protocols, Bye Laws and other legal documents |  |  |  |  | 20000 |  |  |  | On-going | HR Dept | CA | 93
|  | Training of staff (secretaries, adms, HoDs/HoUs on minutes and report writing |  |  |  |  | 15000 | 2000 |  |  | On-going | HR Dept. | CA | 94
|  | Carry out Refresher course for Aspiring Officers due for Promotion and PSC Examination |  |  |  |  | 15000 | 2000 |  |  | On-going | HR Dept. | CA | 95
DEPARTMENT OF STATISTICS
Management and Administration | Planning, Budgeting, Coordination and Statistics | Carry out Quarterly Monitoring of Projects |  |  |  |  | 2000 | 11083 |  |  | On-going | Dvelopment Planning Unit/ Budget Unit | MPCU | 96
|  | Prepare 2023 AAP and Composite Budget/ Fee Fixing/ Procurement Plan and 2022-2025 MTDP |  |  |  |  | 35000 | 12000 |  |  | On-going | Dvelopment Planning Unit/ Budget Unit | MPCU | 97
|  | Update Business data base of the municipality. |  |  |  |  | 2000 | 2882 |  |  | On-going | Statistics Departement | MPCU | 98
|  | Generate administrative data on all departments, Units and agencies |  |  |  |  | 2929 |  |  |  | On-going | Statistics Departement | MPCU | 99